## dbo_Viw_All_JH
PDNP | SubCon | DrawingNo | LineNO | JointNo | Sheet | Area | AG_UG | UNIT | RT | Void | STATUSJOINTHOLD | Rev | JointIndex | TestPackage No | Size | J_Type | J_Status | Des_Status | BaseMaterial | Sch | Thk | Tie In | FitupRep | FitupDate | FitupSubCon | WeldRep | WeldDate | WeldSubCon | Gtaw1 | Smaw1 | Gtaw2 | Smaw2 | WeldRepRepair_Contractor | WeldRepRepair | Repair_Welder1 | Repair_Welder2 | RT NO | RT NO Remark | Report_RT_No | Report_RT_Date | Reslut_RT | RemarkFinal | RT_Contractor | Report_PT_No | Report_PT_Date | PT_Contractor | J_Location | SpoolNo | Percent_Front | Percent_Shop | Percent_Field | Mat0 | Object0 | Mat0-QTY | Received-1 | Shortage-1 | SPL1 | Mat1 | Object1 | Mat1-QTY | Received-2 | Shortage-2 | Hold | HoldRemark | J_Priority | Front | FrontDate | Front Remarks | Sh | J_Service | PipClass | MT_Contractor | Report_MT_No | Report_MT_Date | Remark MT | Hardness | Report_PWHT_No | Report_PWHT_Date | id
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 001 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 14 | BW |  |  | CS | 20 | 7.92 | FALSE | KSB-PH-0039 | 2023-02-03 | KSB | KSB-PH-0033 | 2023-02-05 | KSB | 030 | [17 empty] | F |  |  |  |  | EPFFW62R1801NZZ14S2 | FLANGE WN | 1 | 1 | 0 |  | EPJRESB1601LZZ1410S2S2 | REDUCER ECC | 1 | 1 | 0 |  |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16838
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 002 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0072 | 2023-03-04 | KSB | KSB-PH-0064 | 2023-03-06 | KSB | 021 | [17 empty] | F |  |  |  |  | EPJRESB1601LZZ1410S2S2 | REDUCER ECC | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16839
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 002A | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0082 | 2023-10-04 | KSB | KSB-PH-0072 | 2023-04-10 | KSB | 021 | [17 empty] | F | [6 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 49342
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 002B | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0082 | 2023-10-04 | KSB | KSB-PH-0072 | 2023-04-10 | KSB | 021 | [17 empty] | F | [6 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 49344
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 002C | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0082 | 2023-10-04 | KSB | KSB-PH-0072 | 2023-04-10 | KSB | 021 | [17 empty] | F | [6 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 49346
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 003 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0071 | 2023-03-03 | KSB | KSB-PH-0064 | 2023-03-06 | KSB | 021 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 11.68 | 11.68 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16840
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 003A | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0082 | 2023-10-04 | KSB | KSB-PH-0072 | 2023-04-10 | KSB | 021 | [17 empty] | F | [6 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 49348
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 004 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0071 | 2023-03-03 | KSB | KSB-PH-0062 | 2023-03-04 | KSB | 021 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16841
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 005 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 002 | [7 empty] | 13 |  | KSB-0012 | 2023-01-29 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 3.538 | 3.538 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16842
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 006 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 002 | [7 empty] | 14 |  | KSB-0012 | 2023-01-29 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16843
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 007 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0052 | 2023-02-14 | KSB | KSB-PH-0046 | 2023-02-16 | KSB | 031 | [14 empty] | KSB-PH-0001 | 2023-03-07 | KSB | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16844
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 008 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0054 | 2023-02-16 | KSB | KSB-PH-0047 | 2023-02-17 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16845
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 009 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0051 | 2023-02-13 | KSB | KSB-PH-0046 | 2023-02-16 | KSB | 031 | [7 empty] | 51 | PE2 | KSB-0023 | 2023-02-28 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16846
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 010 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0017 | 2023-01-15 | KSB | KSB-PH-0030 | 2023-01-30 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16847
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 011 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0017 | 2023-01-15 | KSB | KSB-PH-0030 | 2023-01-30 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16848
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 012 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0017 | 2023-01-15 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 031 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16849
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 013 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0017 | 2023-01-15 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 020 | [7 empty] | 22 |  | KSB-0013 | 2023-02-09 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16850
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 014 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0017 | 2023-01-15 | KSB | KSB-PH-0030 | 2023-01-30 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16851
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 015 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0018 | 2023-01-17 | KSB | KSB-PH-0031 | 2023-01-31 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16852
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 016 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0018 | 2023-01-17 | KSB | KSB-PH-0031 | 2023-01-31 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16853
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 017 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0018 | 2023-01-17 | KSB | KSB-PH-0031 | 2023-01-31 | KSB | 004 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16854
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 018 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0018 | 2023-01-17 | KSB | KSB-PH-0038 | 2023-02-07 | KSB | 023 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16855
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 019 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0019 | 2023-01-18 | KSB | KSB-PH-0035 | 2023-02-04 | KSB | 023 | [14 empty] | KSB-PH-0001 | 2023-03-07 | KSB | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16856
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 020 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0022 | 2023-01-21 | KSB | KSB-PH-0035 | 2023-02-04 | KSB | 023 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16857
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 021 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0023 | 2023-01-22 | KSB | KSB-PH-0033 | 2023-02-05 | KSB | 023 | [7 empty] | 23 |  | KSB-0014 | 2023-02-11 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16858
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 022 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0023 | 2023-01-22 | KSB | KSB-PH-0033 | 2023-02-05 | KSB | 023 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 9.165 | 9.165 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16859
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 022-A MAT | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0024 | 2023-01-23 | KSB | KSB-PH-0033 | 2023-02-05 | KSB | 023 | [17 empty] | F | - | [5 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 40458
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 023 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 1 | OLET |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16860
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 024 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 0 | 0 | 0 |  | EPJNLLP1510BZZ01S8 | NIPPLE | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16861
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 025 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJNLLP1510BZZ01S8 | NIPPLE | 0 | 0 | 0 |  | EPVVGB68S0108PEADC1ZZ01 | GATE VALVE | 1 |  | 1 | Mat | [6 empty] | FUG | AAR61 | [7 empty] | 16862
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 026 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPVVGB68S0108PEADC1ZZ01 | GATE VALVE | 0 |  | 0 |  | EPJNLLP1510BZZ01S8 | NIPPLE | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16863
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 027 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJNLLP1510BZZ01S8 | NIPPLE | 0 | 0 | 0 |  | EPFFS62R1801NZZ01S8 | FLANGE SW | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16864
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 028 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0023 | 2023-01-22 | KSB | KSB-PH-0033 | 2023-02-05 | KSB | 023 | [14 empty] | KSB-PH-0001 | 2023-03-07 | KSB | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16865
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 029 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0022 | 2023-01-21 | KSB | KSB-PH-0023 | 2023-01-22 | KSB | 002 | [7 empty] | 24 |  | KSB-0014 | 2023-02-11 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0.438 | 0.438 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16866
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 030 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0022 | 2023-01-21 | KSB | KSB-PH-0023 | 2023-01-22 | KSB | 002 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16867
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 031 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0032 | 2023-01-29 | KSB | KSB-PH-0036 | 2023-02-06 | KSB | 023 | [17 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 5.772 | 5.772 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16868
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 032 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0036 | 2023-02-06 | KSB | 023 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16869
10-FUG-88004-AAR61-H-1/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 033 | 1/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01A | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0032 | 2023-01-29 | KSB | KSB-PH-0036 | 2023-02-06 | KSB | 023 | [17 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16870
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 034 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | OLET |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 6.438 |  | 6.438 |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 1 | 1 | 0 | Mat | [6 empty] | FUG | AAR61 | [7 empty] | 16871
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 035 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 0 | 0 | 0 |  | EPJNLLP1510BZZ01S8 | NIPPLE | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16872
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 036 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJNLLP1510BZZ01S8 | NIPPLE | 0 | 0 | 0 |  | EPFFS62R1801NZZ01S8 | FLANGE SW | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16873
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 037 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0032 | 2023-01-29 | KSB | KSB-PH-0036 | 2023-02-06 | KSB | 023 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16874
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 038 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0038 | 2023-02-07 | KSB | 023 | [17 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 5.771 | 5.771 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16875
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 039 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0038 | 2023-02-01 | KSB | KSB-PH-0038 | 2023-02-07 | KSB | 023 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16876
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 040 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0023 | 2023-01-22 | KSB | 002 | [17 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0.438 | 0.438 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16877
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 041 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0023 | 2023-01-22 | KSB | 002 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16878
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 042 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0038 | 2023-02-01 | KSB | KSB-PH-0038 | 2023-02-07 | KSB | 023 | [17 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 11.384 | 11.384 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16879
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 043 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | OLET |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16880
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 044 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 0 | 0 | 0 |  | EPJNLLP1510BZZ01S8 | NIPPLE | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16881
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 045 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJNLLP1510BZZ01S8 | NIPPLE | 0 | 0 | 0 |  | EPVVGB68S0108PEADC1ZZ01 | GATE VALVE | 1 |  | 1 | Mat | [6 empty] | FUG | AAR61 | [7 empty] | 16882
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 046 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPVVGB68S0108PEADC1ZZ01 | GATE VALVE | 0 |  | 0 |  | EPJNLLP1510BZZ01S8 | NIPPLE | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16883
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 047 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 1 | SW |  |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJNLLP1510BZZ01S8 | NIPPLE | 0 | 0 | 0 |  | EPFFS62R1801NZZ01S8 | FLANGE SW | 1 | 1 | 0 | Under2 |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16884
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 048 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0066 | 2023-02-26 | KSB | KSB-PH-0062 | 2023-03-04 | KSB | 039 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16885
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 049 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0022 | 2023-01-21 | KSB | KSB-PH-0023 | 2023-01-22 | KSB | 002 | [7 empty] | 32 |  | KSB-0016 | 2023-02-14 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0.231 | 0.231 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16886
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 050 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0022 | 2023-01-21 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 002 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  |  |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16887
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 051 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | KSB-PH-0070 | 2023-03-02 | KSB | KSB-PH-0065 | 2023-03-07 | KSB | 039 | [17 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 12 | 0 |  |  |  | DONE |  |  |  | FUG | AAR61 | [7 empty] | 16888
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 052 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | FALSE |  | 01 | N |  | 10 | BW |  |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 |  | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 |  | 12 | TIE-IN | [6 empty] | FUG | AAR61 | [7 empty] | 16889
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 053 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16890
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 054 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16891
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 055 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16892
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 056 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16893
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 057 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16894
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 058 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16895
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 059 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16896
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 060 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16897
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 061 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 12 | 0 | 12 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16898
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 062 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 6.382 | 0 | 6.382 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16899
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 063 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 1 | OLET | Cancel |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 1 | 1 | 0 | Under2 | Out Of Scope |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16900
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 064 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 1 | SW | Cancel |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJOSFS1801OZZ1001L3 | SOCKOLET | 0 | 0 | 0 |  | EPJNLLP1510BZZ01S8 | NIPPLE | 1 | 1 | 0 | Under2 | Out Of Scope |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16901
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 065 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 1 | SW | Cancel |  | CS | 80 | 4.55 | FALSE | [24 empty] | F |  |  |  |  | EPJNLLP1510BZZ01S8 | NIPPLE | 0 | 0 | 0 |  | EPFFS62R1801NZZ01S8 | FLANGE SW | 1 | 1 | 0 | Under2 | Out Of Scope |  | Front |  |  |  | FUG | AAR61 | [7 empty] | 16902
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 066 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16903
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 067 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Delete |  | CS | 20 | 6.35 | FALSE | KSB-PH-0021 | 2023-01-20 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 002 | [7 empty] | 45 | PE1 | KSB-0025 | 2023-03-09 | ACC |  | KSB |  |  |  | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0.838 | 0 | 0.838 |  | Out Of Scope |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16904
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 068 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Delete |  | CS | 20 | 6.35 | FALSE | KSB-PH-0022 | 2023-01-21 | KSB | KSB-PH-0024 | 2023-01-23 | KSB | 002 | [7 empty] | 45 | PE2 | KSB-0025 | 2023-03-09 |  |  | KSB |  |  |  | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 1 | 1 | 0 |  | Out Of Scope |  | Old Done |  |  |  | FUG | AAR61 | [7 empty] | 16905
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 069 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Cancel |  | CS | 20 | 6.35 | FALSE | [24 empty] | F |  |  |  |  | EPJELSB1601LZZ10S2 | ELBOW 90 | 0 | 0 | 0 |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 10.608 | 0 | 10.608 | Mat | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16906
10-FUG-88004-AAR61-H-2/2 | KSB | KP-99-99-DD-PI-ISO-0002 | 10-FUG-88004-AAR61-H | 070 | 2/2 | RACK(N-HDPE) | AG | HDPE | 10 | TRUE |  | 01 | N |  | 10 | BW | Delete |  | CS | 20 | 6.35 | FALSE | KSB-PH-0045 | 2023-02-07 | KSB | KSB-PH-0061 | 2023-03-03 | KSB | 021 | [17 empty] | F |  |  |  |  | EPPPSB1510AZZ10S2 | PIPE SMLS | 0 | 0 | 0 |  | EPFFW62R1801NZZ10S2 | FLANGE WN | 1 | 1 | 0 |  | Out Of Scope | [5 empty] | FUG | AAR61 | [7 empty] | 16907