## Information
General Data |  | MAP Information
CONTRACTOR | OmranSahel | No. | P&ID No. | REV. | LINE No. | REV. | Sheet | ISO DWG No.
SUBSYSTEM NO. | 99003 | 1 | KP-99-00-DD-PR-PID-8101 | 01 | 3-PRY-88011-BAR01-N(PHASE2) | 01A | 1 | 88011
AREA | 1 | 2 | KP-99-00-DD-PR-PID-8101 | 01 | 3-PRY-88011-BAR01-N(PHASE2) | 01A | 2 | 88011
UNIT | 88 |  | KP-99-00-DD-PR-PID-8101 | 01 | 3-PRY-88012-BAR01-N(PHASE2) | 01 | 1 | 88012
AREA-UNIT | 1/88
MATERIAL CLASS | BAR01
SYSTEM | PRY
COMPONENT ID: | 898
FROM: | OLEFIN TANK FARM
TO: | FIRST HDPE PLANT
TRAIN :
SIZE : | 3
LOCATION : | AG- UNIT 88
TEST PACKAGE NO. | 99003-AG-PRY-001-00
TEST MEDIUM | WATER
TEST PRESSURE | 36.6
ELEVATION FROM | 109975
ELEVATION TO | 111744

## CHECK LIST OK-1
OFFSITE PROJECT BASIC DESIGN PHASE
TEST PACKAGE CHECK LIST
SUBSYSTEM NO. |  | 99003 |  | TEST PACKAGE NO. | 99003-AG-PRY-001-00
ITEM | DESCRIPTION |  |  |  |  | ACC | REJ | N/A
1 | ISOMETRIC REVIEW |  | DATE 1. 2. 3.
COMMENT:
2 | P&ID REVIEW |  | DATE 1. 2. 3.
COMMENT:
3 | LINE LIST REVIEW AND MARK UP |  | DATE 1. 2. 3.
COMMENT:
4 | ISOMETRIC MARK UP REVIEW |  | DATE 1. 2. 3.
COMMENT:
5 | P&ID MARK UP REVIEW |  | DATE 1. 2. 3.
COMMENT:
6 | SUPPORT LIST REVIEW |  | DATE 1. 2. 3.
COMMENT:
7 | FORMAT SHEET REVIEW |  | DATE 1. 2. 3.
COMMENT:

## COVER SHEET-008-OK
TEST PACKAGE COVER SHEET
TEST PACKAGE NO.: |  | 99003-AG-PRY-001-00
UNIT / SUBUNIT : | 88
TEST MEDIUM: | WATER
TEST PRESSURE (Barg.): | 36.6
PRESSURE GAUGE : CALIBRATION DATE & NUMBERS
VOLUME OF WORK (DIA IN): | 898
REMARKS:
PIP-008

## Check List (hidden)
Test Package Finalize Requirement Punching Check List
Test Package NO.: |  |  | #REF!
Percent of Progress in Check List Preparation Time:
Percent of Progress in Checking Time:
Description
No. | Inspection Item | Status of Inspection |  |  |  | Date of First Check | Responsible Department (Check by)
|  | OK | NIS | N/A | Final
1 | Cover Sheet Preparation
2 | Welded Material
3 | Miscellaneous Material
4 | Equipment Control
5 | Pipe Support
Remarks:
| Internal Punching | [5 empty] | JP Piping Technical Office
JAHANPARS
Eng. & Const. Co. (Pvt)
JAHANPARS
Eng. & Const. Co. (Pvt)

## TEST PACKAGE INDEX-020-OK
TEST PACKAGE INDEX
TEST PACKAGE NO. |  |  | 99003-AG-PRY-001-00 |  | AREA/ UNIT |  | 1/88
ITEM | FORM No. | DESCRIPTION |  | APPLICABLE |  | NOT APPLICABLE
1 | PIP-008 | TEST PACKAGE COVER SHEET |  | P |  |  |  | page
2 | PIP-020 | TEST PACKAGE INDEX |  | P
3 | PIP-010 | RELEASE NOTE FOR PIPING TEST PACKAGE ACTIVITY SHEET |  | P |  |  |  | page
4 | PIP-005 | PUNCH LIST |  | P |  |  |  | page
5 | PIP-011 | CLEANING |  | P
6 | PIP-027 | MECHANICAL COMPLETION CHECK LIST |  | P |  |  |  | page
7 | PIP-028 | PIPING INSPECTION CHECK LIST |  | P |  |  |  | page
8 | PIP-007 | PIPING PRESSURE TEST REPORT |  | P |  |  |  | page
9 | ATTACH. | LINE LIST |  | P
10 | ATTACH. | PRESSURE GAUGE CALIBRATION/RECORDER CERTIFICATE |  | P |  |  |  | Page
11 | PIP-024 | REINSTATEMENT REPORT |  | P |  |  |  | page
12 | PIP-021 | REINFORCING PAD TEST REPORT |  |  |  | P |  | page
13 | PIP-023 | DRAINING & DRYING |  | P |  |  |  | page
14 | PIP-022 | FLUSHING / DRYING REPORT |  | P |  |  |  | page
15 | PIP-018 | TIE IN JOINT LIST SUMMARY |  |  |  | P |  | Page
16 | PIP-025 | ORIFICE FLANGE INSPECTION REPORT |  |  |  | P |  | Page
17 | PIP-026 | SUPPORT LIST |  | P |  |  |  | page
18 | PIP-019 | FIELD SITE QUERY (FSQ)/DCN |  |  |  | P
19 | ATTACH. | PARALLEL WITH EQUIPMENT FLANGE ( IF REQ. ) |  |  |  | P
20 | ATTACH. | WATER ANALYSIS REPORT ( IF REQ. ) |  |  |  | P
21 | ATTACH. | JOINT HISTORY SHEET ( APPROVED BY : CONTRACTOR QC ) |  | P
22 | ATTACH. | ISO DRAWING (AS-BUILT) ( SIGNATURE BY DCC. ) |  | P
23 | ATTACH. | MARKED-UP P&ID ( SIGNATURE BY PRE DCC ) |  | P
24 | ATTACH. | COMPOSITE PLAN DRAWING |  |  |  | P
FORM No.: PIP-020

## RELEASE NOTE-10-OK
RELEASE NOTE FOR PIPING TEST PACKAGE ACTIVITY SHEET
TEST PACKAGE No. |  |  |  | 99003-AG-PRY-001-00
CONTRACTOR | OmranSahel | AREA/UNIT |  | 1/88
ACTIVITY |  | COMPLETION CONFIRMATION
|  | CONTRACTOR | OWNER
|  | OmranSahel | SUPERVISION |  | TECHNICAL INSPECTION
|  | NAME/DATE | NAME/DATE |  | NAME/DATE
MECHANICAL COMPLETION CHECK LIST
REINFORCING PAD TEST REPORT
PUNCH "A" (RELEASE FOR PRESSURE TEST)
CLEANING
PRESSURE TEST
DRAINING & DRYING
FLUSHING & BLOWING
PUNCH "B" (RELEASE FOR COMMISSIONING)
REINSTATEMENT (RELEASE FOR PAINTING/INSULATION)
PUNCH "C" (CAN BE DONE AFTER COMMISSIONING )
FORM No : PIP-010

## PUNCH LIST-005-OK
PUNCH LIST
TEST PACKAGE NO. |  |  | 99003-AG-PRY-001-00 |  |  | AREA/ UNIT | 1/88 | CONTRACTOR |  | OmranSahel | SHEET | OF
ITEM | ISO DWG. NO. | DESCRIPTION OF PUNCH ITEM(S) |  |  | PUNCH | ORIGINATOR | COMPLETION DATE | STATUS OF CONFIRMATION
[8 empty] | CONTRACTOR | OWNER(SUPERVISION) | OWNER (TECHNICAL INSPECTION) | EIED
PUNCH ITEM(S) A : ITEM TO BE WORKED OFF BEFORE HYDROTEST B : ITEM TO BE WORKED OFF AFTER HYDROTEST AND BEFORE PRE-COMM. C : ITEM CAN BE WORKED OFF AFTER PRE-COMM.
|  | CONTRACTOR |  |  |  |  | OWNER
|  | SUPERVISION |  | QC |  |  | SUPERVISION |  |  | TECHNICAL INSPECTION
NAME
DATE
SIGNATURE
FORM No.: PIP-005

## CLEANING-OK
CLEANING
TESTPAKAGE No. |  |  | 99003-AG-PRY-001-00 | AREA/UNIT |  | 1/88 |  | REPORT No. :
|  |  |  | CONTRACTOR |  | OmranSahel |  | DATE:
INSPECTION TYPE |  |  | BEFORE HYDROTEST
CLEANING METHOD |  |  | AIR BLOWING |  | WATER FLUSHING |  |  |  | STEAM OUT
|  |  | OIL FLUSHING |  | CHEMICHAL CLANING
ITEM | LINE NUMBER |  |  | CLEANINIG |  | RESULT |  |  | REMARKS
|  |  |  | MEDIA | RATE | ACC | REJ
1 | 3-PRY-88011-BAR01-N(PHASE2)
2 | 3-PRY-88011-BAR01-N(PHASE2)
3 | 3-PRY-88012-BAR01-N(PHASE2)
0
0
0
0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
COMMENTS:
|  | CONTRACTOR |  |  |  | OWNER
|  | Exir Sanat |  |  |  | SUPERVISION
NAME
SIGNATURE
DATE
PIP-011

## MECHANICAL COMPLETION-027 -OK
CONSTRACTION MECHANICAL COMPLETION CHECK LIST
TEST PACKAGE No. |  |  | 99003-AG-PRY-001-00 |  |  |  | CON. |  | OmranSahel |  | AREA/ UNIT | 1/88
NO. | INSPECTION ITEM |  |  | CONTRACTOR |  | OWNER (SUPERVISION) |  |  |  | OWNER (TECHNICAL INSPECTION)
|  |  |  | Acc. | Rej. | Acc. |  | Rej. |  | Acc. |  | Rej.
1 | MECHANICAL CLEARANCE
A) CONFORMITY WITH DRAWING
B) VENT AND DRAIN FOR HYDROTEST
C) EQUIPMENT TO BE ISOLATED
2 | WELDING AND NDT CLEARANCE
A) MATERIAL AS PER PIPING CLASS
B) VISUAL CHECK OF COMPLETION WELD
C) ARC STRIKE REMOVED
D) PT/MT/UT
E) RADIOGRAPHY EXAMINATION
F) REINFORCING PAD TEST
3 | SUPPORT COMPLETION
A) CONFORMITY WITH DRAWING
B) VISUAL CHECK OF COMPLETION
NOTE: ITEMS No.1&3 TO BE COMPLETED BY HYDRO TEST TEAM. ITEM No. 2 TO BE COMPLETED BY QC TEAM. P ACC __ N/A
|  | CONTRACTOR |  |  | OWNER
|  | Exir Sanat |  |  | SUPERVISION |  |  |  | TECHNICAL INSPECTION
NAME
SIGNATURE
DATE
FORM No. : PIP : 027

## PIPING INSPEC. CHECK LIST-0 (2
PIPING INSPECTION CHECK LIST
TEST PACKAGE NO. |  | 99003-AG-PRY-001-00 |  |  | CON. | OmranSahel | AREA/UNIT | 1/88
ITEM | ITEMS TO CHECK |  | CONTRACTOR |  | OWNER (SUPERVISION)
1 | PIPING MATERIALS AS PER SPECIFICATION
2 | SYSTEM COMPLIES WITH P&ID AND ISOMETRIC
3 | SUPPORT COMPLETED (SHOE, ANCHOR, GUIDE, ETC.)
4 | SUPPORT SEAT IS CORRECT
5 | TEMPORARY GASKET INSTALLED
6 | TEMPORARY SPADE/BLIND/SPOOL INSTALLED
7 | TEMPORARY SUPPORT FOR HYDROTEST(IF ANY)
8 | TEMPORARY BLIND FLANGE(IF ANY)
9 | NUT AND BOLT TORQUE TIGHTENED & CORRECT SIZE
10 | FLOW DIRECTION OF VALVE CORRECT(CHECK,GLOBE, ETC.)
11 | VENT & DRAIN CORRECT
12 | SPRING HANGER/SUPPORT INSTALLED & LOCKED
13 | SAFETY RELIEF VALVE REMOVED
14 | CONTROL VALVE BY-PASSED/REMOVED
15 | STRAINER AND FILTER REMOVED
16 | CHECK VALVE FLAPPER REMOVED/LOCK OPEN
17 | IN LINE INSTRUMENT ITEM REMOVED
18 | ORIFICE PLATE REMOVED (EXCLUDE IN FLUSHING/TESTING)
19 | INSIDE OF ORIFICE FLANGE GRIND AS PER REQUIRED
20 | ORIANTATION OF ORIFICE FLANGE TAPPING IS CORRECT
21 | PLUG REMOVED FROM TELL-TAIL HOLE
22 | FLANGE DISCONNECTED FROM EQUIPMENT
23 | FLANGE ALIGNMENT CORRECT
24 | AS-BUILT CONDITION AND RECORD CHECKED
25 | WELDING AND NDT COMPLETED AS PER ISO DWG'S
26 | VALVE TAG NO CORRECT
27 | VALVE STEM ORIENTATION CORRECT
28 | VALVE OPERATION CORRECT
29 | LINE SPACING ALIGNMENT CORRECT
30 | THE SLOPE OF THE LINE IS CORRECT
31 | ORIANTATION OF JACK BOLT IS CORRECT
NOTE: FILL IN THE ABOVE BLANKS AS EXAMPLE: P ACC __ N/A
|  | CONTRACTOR |  | OWNER
|  | Exir Sanat |  | SUPERVISION
NAME
DATE
SIGNATURE
FORM No.: PIP-028

## PRESSURE TEST REPORT-007-OK
PIPING PRESSURE TEST REPORT
AREA / UNIT | 1/88 | 99003-AG-PRY-001-00 |  | TEST PRESSURE (BAR) |  | 36.6 |  | REPORT No.
CON. | OmranSahel | MATERIAL CLASS | BAR01 |  |  |  |  | DATE
ELEVATION |  | FROM | OLEFIN TANK FARM | TO | FIRST HDPE PLANT |  |  | SHEET | 1 | 1
| GAUGE SERIAL No. | MEASURING RANGE (BAR) |  | CALIBRATION DATE |  |  |  | TEST SCHEDULE
High Point | [7 empty] | START TIME
Low Point | [7 empty] | FINISH TIME
Manifold | [7 empty] | HOLDING TIME(Min)
No. | P&ID No. | REV. | LINE No. | ISO DWG No. |  |  | REV. | SHEET | FINAL STATUS
[9 empty] | Acc. | Rej.
1 | KP-99-00-DD-PR-PID-8101 | 01 | 3-PRY-88011-BAR01-N(PHASE2) | 88011 |  |  | 01A | 1
2 | KP-99-00-DD-PR-PID-8101 | 01 | 3-PRY-88011-BAR01-N(PHASE2) | 88011 |  |  | 01A | 2
3 | KP-99-00-DD-PR-PID-8101 | 01 | 3-PRY-88012-BAR01-N(PHASE2) | 88012 |  |  | 01 | 1
4 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | 0 | 0 | 0 |  |  |  | 0 | 0
9 | 0 | 0 | 0 |  |  |  | 0 | 0
10 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Remarks:
| CONTRACTOR |  | OWNER
| Exir Sanat |  | SUPERVISION |  |  | TECHNICAL INSPECTION
NAME
SIGNATURE
DATE
FORM NO.: PIP: 007
OF

## RECORD TOLERANCE -013-OK
RECORD TOLERANCE PRESSURE GAUGE IN HYDROTEST PERIOD
Gauge No.: ………………………... |  |  |  |  | Test Package No. : | 99003-AG-PRY-001-00
Start Time : ………………………... |  |  |  |  | Date: …………………………
NO | TIME | TOLERANCE BARG |  | TEMP | START TIME HOLDING : TOLERANCE PRESSURE : FINISH TIME : TOLERANCE PRESSURE :
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
| CONTRACTOR |  | OWNER
| OmranSahel |  | SUPERVISION |  |  | TECHNICAL INSPECTION
Name:
Sign.:
Date:
[7 empty] | Form No.: | PIP-013

## PRESSURE GAUGE REPORT -006-OK
PRESSURE GAUGE CALIBRATION RECORD
TEST PACKAGE NO: |  |  | 99003-AG-PRY-001-00 |  | AREA/UNIT: | 1/88
CONTRACTOR: | OmranSahel | DISCIPLINE : |  | REPORT NO.: |  | DATE:
TEST GAUGE NO. | RANGE |  | COMPLETION CONFIRMATION
|  |  | CONTRACTOR |  | OWNER
|  |  | Exir Sanat |  | SUPERVISION | TECHNICAL INSPECTION
REMARK :
| CONTRACTOR |  | OWNER
| Exir Sanat |  | SUPERVISION |  | TECHNICAL INSPECTION
Name:
Sign:
Date:
Form No.:PIP-006

## REINSTATEMENT REPORT-024-OK
REINSTATEMENT REPORT
TEST PACKAGE NO. |  |  | 99003-AG-PRY-001-00 |  | CON. | OmranSahel | AREA/ UNIT | 1/88
ITEM | INSPECTION ITEMS |  |  |  | CONTRACTOR | OWNER (SUPERVISION)
1 | LATEST REVISION OF ALL DOCUMENTS INSERTED
2 | TEMPORARY BLIND FLANGE/SPADE / SPOOL REMOVED
3 | TEMPORARY GASKET REPLACED WITH ORIGINAL GASKET
4 | TEMPORARY SUPPORT REMOVED (IF ANY PROVIDED FOR TEST)
5 | SUPPORT COMPLETED (SHOE, ANCHOR, GUIDE, ETC.)
6 | TEMPORARY BOLT & NUT REPLACED WITH CLEANED ORIGINAL BOLT & NUT AND TIGHTENED
7 | CAP/PLUG REINSTALLED(AND SEAL WELDED IF REQUIRED)
8 | INSTRUMENT IN-LINE ITEM REINSTALLED
9 | SPRING SUPPORT ALIGNMENT (COLD SETTING/EXPANSION BELLOW SETTING)
10 | ROTATING EQUPMENT FLANGE CONNECTION WITHIN TELORANCE (FINAL ALIGNMENT)
11 | VALVE INSTALLATION AND DIRECTION CHECKED
12 | VALVE OPERATION CORRECT
13 | HANDLE AND LOCK FOR VALVE INSTALLED
14 | SAFETY RELIEF VALVE INSTALLED (WITH TEMPORARY GASKET)
15 | CONTROL VALVE REINSTALLED
16 | SHUT-OFF VALVE REINSTALLED
17 | STRAINER/FILTER REINSTALLED (MESH AFTER PERCOM FLUSHING)
18 | STEAM TRAP REINSTALLED (AFTER STEAM OUT)
19 | TRACER LINE COMPLETED
20 | INSULATION KIT INSTALLED
21 | BELLOW REINSTALLED
22 | BURSTING DISC INSTALLED
23 | CHECK VALVE FLAPPER REINSTALLED (AFTER PRECOM FLUSHING)
24 | ORIFICE PLATE / RO INSTALLED
25 | ORIFICE FLANGE TAPPING SEAL WELDED (IF REQUIRED)
26 | TELLTALE PLUG REINSTALLED AND SEALD
27 | SPECTICALE / FIGURE 8 / RING SPACER DIRECTION AS PER DWG.
28 | BIRD SCREEN INSTALLED (IF REQUIRED)
NOTE: FILL IN THE ABOVE BLANKS AS EXAMPLE: P CHECKED __ N/A
|  | CONTRACTOR |  | OWNER
|  | OmranSahel |  | SUPERVISION
NAME
SIGNATURE
DATE
FORM No.PIP-024

## REINFORCING PAD-021 (hidden)
|  |  | South Pars Gas Field Development Phases 22,23 &24 | [5 empty] | Pars Oil & Gas Company
REINFORCING PAD TEST REPORT
SUBSYSTEM No. |  | #REF! |  | GAUGE SERIAL No. |  |  |  | REPORT No.
TEST PACKAGE No. |  | #REF! |  | CALIBRATION DATE |  |  |  | DATE
SUBCONTRACTOR |  | #REF! |  |  |  |  | MEASURING RANGE (BAR)
ITEM | ISO DWG. No. |  | LINE No. | SHEET | REV. | SPOOL No. | JOINT No. | WELD TYPE | TEST PRESS. (Bar) | RESULT
[10 empty] | Acc. | Rej.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
COMMENTS:
|  |  | SUBCON. | CONTRACTOR |  |  |  | TPA / COMPANY
NAME
SIGNATURE
DATE
FORM No. : PIP-021

## REINFORCING PAD-021 (2)-OK
REINFORCING PAD TEST REPORT
TEST PACKAGE No. |  | 99003-AG-PRY-001-00 |  | GAUGE SERIAL No. |  |  |  | REPORT No.
|  |  |  | CALIBRATION DATE |  |  |  | DATE
CONTRACTOR |  | OmranSahel |  |  |  |  | MEASURING RANGE (BAR)
ITEM | ISO DWG. No. |  | LINE No. | SHEET | REV. | SPOOL No. | JOINT No. | WELD TYPE | TEST PRESS. (Bar) | RESULT
[10 empty] | Acc. | Rej.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
COMMENTS:
|  |  | CONTRACTOR | OWNER
|  |  | OmranSahel | SUPERVISION |  |  |  | TECHNICAL INSPECTION
NAME
SIGNATURE
DATE
FORM No. : PIP-021

## DRAINING & DRYING-023-OK
DRAINING / DRYING AFTER HYDROSTATIC TEST
TEST PACKAGE NO: | [7 empty] | 99003-AG-PRY-001-00
CONTRACTOR : |  | OmranSahel |  |  | REPORT NO : |  |  |  | DATE
ITEM | ISO DWG. NO. | LINE NUMBER | SH | Rev. | DRYING |  | DATE |  | RESULT |  | REMARKS
[5 empty] | MEDIA | RATE | START | END | Acc. | Rej.
1 | 88011 | 3-PRY-88011-BAR01-N(PHASE2) | 1 | 01A
2 | 88011 | 3-PRY-88011-BAR01-N(PHASE2) | 2 | 01A
3 | 88012 | 3-PRY-88012-BAR01-N(PHASE2) | 1 | 01
4 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0
8 |  | 0 | 0 | 0
9 |  | 0 | 0 | 0
10 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0
13 | 0 | 0 | 0 | 0
14 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0
16 | 0 | 0 | 0 | 0
17 | 0 | 0 | 0 | 0
18 | 0 | 0 | 0 | 0
COMMENTS:
|  | CONTRACTOR |  |  |  |  | OWNER
|  | OmranSahel |  |  |  |  | SUPERVISION
NAME
DATE
SIGNATURE
FORM No. : PIP-023

## FLUSHING & BLOWING -022-OK
FLUSHING & BLOWING AFTER HYDROSTATIC TEST
TEST PACKAGE No. |  |  | 99003-AG-PRY-001-00 | REPORT NO. |  |  | DATE |  | AREA /UNIT | 1/88 | REPORT NO.
NO. | ISO DWG. NO. |  | LINE NO. | SH | REV. | RESULT
[6 empty] | ACCEPT |  | REJECT
1 | 88011 |  | 3-PRY-88011-BAR01-N(PHASE2) | 1 | 01A
2 | 88011 |  | 3-PRY-88011-BAR01-N(PHASE2) | 2 | 01A
3 | 88012 |  | 3-PRY-88012-BAR01-N(PHASE2) | 1 | 01
4 | 0 |  | 0 | 0 | 0
5 | 0 |  | 0 | 0 | 0
6 | 0 |  | 0 | 0 | 0
7 | 0 |  | 0 | 0 | 0
8 | 0 |  | 0 | 0 | 0
9 | 0 |  | 0 | 0 | 0
10 | 0 |  | 0 | 0 | 0
11 | 0 |  | 0 | 0 | 0
12 | 0 |  | 0 | 0 | 0
13 | 0 |  | 0 | 0 | 0
14 | 0 |  | 0 | 0 | 0
15 | 0 |  | 0 | 0 | 0
16 | 0 |  | 0 | 0 | 0
17 | 0 |  | 0 | 0 | 0
COMMENT: FILL IN THE ABOVE BLANKS AS EXAMPLE: P CHECKED __ N/A
|  | CONTRACTOR |  | OWNER
|  | OmranSahel |  | SUPERVISION
NAME
DATE
SIGNATURE
FORM NO. : PIP-022

## ORIFICE FLANGE GRIND FLUSH -025 (hidden)
|  |  | SOUTH PARS GAS FIELD DEVELOPMENT Phases 22 , 23 & 24 | [5 empty] | Pars Oil & Gas Company
INSPECTION REPORT FOR ORIFICE INTERNAL WELD FLUSH GRINDING
SUBSYSTEM NO. |  | #REF! |  | TEST PACKAGE NO. | #REF! |  |  | AREA/ UNIT |  | #REF!
ITEM | ISO DWG. NO. |  | FLANGE TAG NO. |  | SHT. | REV. | JOINT NO. | SIZE |  | REMARKS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
COMMENTS:
|  |  | SUBCONTRACTOR |  | CONTRACTOR |  |  | TPA / COMPANY
NAME:
DATE:
SIGNATURE:
FORM No.PIP-025

## TIE IN JOINT LIST SUMMARY-018-O
TIE IN JOINT LIST SUMMARY
TEST PACKAGE NO. |  |  | 99003-AG-PRY-001-00 |  |  |  | AREA/ UNIT | 1/88
ITEM | ISO DWG. NO. | LINE NO. |  | SHEET | REV. | JOINT NO. | NDT RESULT | PWHT RESULT | REMARKS | #VALUE!
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
COMMENTS:
|  | CONTRACTOR |  | OWNER
|  | OmranSahel |  | SUPERVISION |  |  |  | TECHNICAL INSPECTION |  |  | STD-181 | UB-AA1 | 1 | 1
NAME: | [10 empty] | STD-181 | UB-AA1 | 1 | 1
DATE: | [10 empty] | STD-242 | PS02-B1(L=160)(H=460 | 1 | 1
SIGNATURE: | [10 empty] | STD-242 | PS02-B1(L=160)(H=460 | 1 | 1
FORM No.PIP-018

## ORIFICE FLANGE GRIND FLUSH (2-
INSPECTION REPORT FOR ORIFICE INTERNAL WELD FLUSH GRINDING
TEST PACKAGE NO. |  |  | 99003-AG-PRY-001-00 |  |  |  | AREA/ UNIT |  | 1/88
ITEM | ISO DWG. NO. | FLANGE TAG NO. |  | SHT. | REV. | JOINT NO. | SIZE |  | REMARKS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
COMMENTS:
|  | CONTRACTOR |  |  |  | OWNER
|  | OmranSahel |  |  |  | SUPERVISION
NAME:
DATE:
SIGNATURE:
FORM No.PIP-025
| AM-101-20008 | [5 empty] | 12-AM-101-20008-B48-N

## SUPPORT LIST-026
KANGAN UTILITY & OFFSITE PROJECT BASIC DESIGN PHASE
SUPPORT LIST
TEST PACKAGE NO. |  |  |  | 99003-AG-PRY-001-00 |  |  | AREA/ UNIT | 1/88 |  | PAGE 1 | OF | 1
ITEM | ISO DWG NO. | Rev. | SH | LINE NO. |  | SUPPORT DWG NO. |  |  | REV. | SUPPORT TYPE | SUPPORT SIZE |  | QTY.
1 | KP-10-14-DD-PR-PID-14002 |  | 1 | 1-WFG-14160-AAR61-N(BY-SITE) |  |  |  |  | 00B | GBU | 1 |  | 4
2 | KP-10-14-DD-PR-PID-14002 |  | 1 | 1-WFG-14161-AAR61-N |  |  |  |  | 01B | GBU | 1 |  | 5
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
COMMENTS:
|  | CONTRACTOR |  |  | OWNER
|  | OmranSahel |  |  | SUPERVISION |  |  |  | TECHNICAL INSPECTION
NAME
DATE
SIGNATURE
FORM NO.: PIP-026

## WARNING TAG-011
KANGAN UTILITY & OFFSITE PROJECT BASIC DESIGN PHASE
WARNING TAG FOR HYDROSTATIC & PENUMATIC TEST
DANGER
HYDROSTATIC PRESSURE TEST
TEST IN PROGRESS
DO NOT OPERATE
SYSTEM: |  | HYDROTEST
COMPONENT ID: |  | 898
DATE:
TEST ENGINEER:
TEST NO : |  | 99003-AG-PRY-001-00
FORM NO.: PIP-011