## ITP FIX
NO. | INSPECTION/TEST ITEM | Reference Documents | Verifying Document | INSPECTION POINT |  | Remark
|  |  |  | CONTRACTOR | COMPANY
A‐A | Equipment / Material check | MTC & Project Specification & DWG | Form No. 16 | H | W
IRN Packing List Check Physical Condition For Damage, Dent, Corrosion Review Mill Certificate (MTC) Plate checking Bolt /Nuts and sliding Plate checking Storage condition
A‐B | Padding Elevation | Related Drawing | Form No. 01 | H | RA
 Check the Padding elevation
A‐C | Pre‐Erection | Project Specification & DWG | Form No. 02 | H | H
 Release from Civil/Stl.Str QC for installation Foundation Marking  Backfilling Completion  Check the Anchor bolt position /Projection and cleanliness  Check the Chipping condition
A‐D | Equipment Erection | Project Specification & DWG | Form No. 03 Form No. 04 | H | W
Orientation and Location Check Elevation Check Checking Anchor bolt projection,tightening and shim plate filling  Check Plumpness  Level Check
NO. | INSPECTION/TEST ITEM | Reference Documents | Verifying Document | INSPECTION POINT |  | Remark
|  |  |  | CONTRACTOR | COMPANY
A‐E | Grouting of Base Plate | Project Specification & DWG | Form No. 05 | H | H
 Preparation Condition, Surface Cleaning, Water Socking, Grouting material verification, Pouring water verification Temperature, Shim Plate Spot welding, Check drain  Mixing and pouring  Curing and Preservation  Pocket grouting (if required)
A‐F | Anchor Bolt Tightening | Project Specification & DWG | Form No. 06 | H | H
A‐G | Fit Up & Welding Inspection (if required) | Project Specification | Form No. 07 Form No. 08 | Refer to Applicable Items in inspection & test plan for atmospheric tank work (All inspections shall be done by welding inspector)
 Fit-Up Condition (Alignment, Root Gap, Cleaning, Etc.)  Applicable WPS/Welder/Welding Consumable / WPS And Welder ID  Electrode / Filler Check  Essential Variable Check  Preheating (if required)  Visual Inspection  NDT (if required)  Repair (if required)
A‐H | All necessary Appurtenance Installation | Related DWG | Form No. 09 | H | H W
 Bolt Tightening  Plat Form  Grating Top Davit Safty Gate
A‐I | Hydrotest (If Requaired) | Hydrotest Procedures | Form No. G-01 | H | H
 Hydrotest Execution  Hydrotest Report
A‐J | Painting(If Required) (According to inspection & test plan for paint work Doc.) | Project Specification
A-K | Final Inspection | Project Specification & DWG | Form No. 18 Form No. 34 | H | H
|  Visual Checking(shortage/damages)  Sliding Side Clearance Checking(Horizontal Equipments)  Touch Up(If Requaired) External installation Completion  Name Plate Verification  Grouting Final Surface Condition  Final bolt Tightening  Washer Welding  Punch List Clarify(if required) |  |  |  | H
NO. | INSPECTION/TEST ITEM | Reference Documents | Verifying Document | INSPECTION POINT |  | Remark
|  |  |  | CONTRACTOR | COMPANY
B | INTERNAL ACTIVITIES
B‐A | MATERIAL RECEIVING INSPECTION (MRI) | MTC & Project Specification & DWG | Form No. 16 | H | W
B‐B | INTERNAL CHECKING | Project Specification & DWG | Form No. 10 | H | SW
 VISUAL INSPECTION OF INSIDE CONDITION  CORROSION CHECKING
B‐C | INTERNAL INSTALLATION | Project Specification & DWG | Form No.11 Form No.12 | H | SW
INTERNAL ACCESSORIES INSTALLATION INTERNAL FILLING
B‐D | TRAY MEASURMENT & ASSOCIATED | Project Specification & DWG | Form No. 13 | H | H
 TRAY DIAMETER  TRAY TO SHELL DISTANCE  TRAY LEVELING(BY MANOMETER)  TRAY SAGGING  BAFFLE PLATE HEIGHT/OUTLET WEIR HEIGHT  DISTANCE BETWEEN TRAY AND DOWNCOMER  HEIGHT OF DOWNCOMER  BDH VALVE DISTANCE  BOLT TIGHTENING CONTROL  CLAMP TIGHTENING CONTROL  TRAY TO SUPPORT CLEARANCE FILLING  DISTANCE BETWEEN TRAY AND SUPPORT RING  LEVELING OF WEIR HORIZONTALITY OF SUPPORT RING  GASKET CHECKING
B‐E | BOLT TIGHTENING | Project Specification & DWG | Form No. 06 | H | H
B‐F | INTERNAL PACKING (IF REQUIRED)٭ | Project Specification & DWG | Form No. 14 | H | W
 MATERIAL VERIFICATION  HEIGHT/VOLUME OF PACKING
B‐G | WELDING(if Required) | Project Specification & DWG | Form No. 08 | H | Refer to Applicable Items in inspection & test plan for atmospheric tank work (All inspections shall be done by welding inspector)
B‐H | TRAY LEAKAGE TEST(IF REQUIRED) | Project Specification & DWG | Form No. 15 | H | H
 GASKET CHECKING (IF REQUIRED)
B‐I | FINAL BOX UP٭ | Project Specification & DWG | Form No. 17 Form No. 34 | H | H
 INSIDE CLEANING  MANWAY CLOSING &BOLT  ORIGINAL GASKET INSTALLATION  MANHOLE BOLT TIGHTENING(BALANCED)  STUD BOLT PRESERVATION  NDT RESULT ATTACHED  LEAK TEST RESULT ATTACHED(IF REQUIRED)  ALL INTERNAL ASSOCIATED INSTALLATION  PUNCH LIST CLEARING ATTACHED  ALL CONNECTIONS BLINDED CHECKING
EX: Executer R: Review SW: Spot Witness W: Witness H: Hold N/A: Not Applicable

## ITP ROTARY
NO. | INSPECTION/TEST ITEM | Reference Documents | Verifying Document | INSPECTION POINT |  | Remark
|  |  |  | CONTRACTOR | COMPANY
A‐A | Equipment / Material check | MTC & Project Specification & DWG | Form No. 16 | H | W
IRN Packing List Check Physical Condition For Damage, Dent, Corrosion Review Mill Certificate (MTC) Plate checking Bolt /Nuts and sliding Plate checking Storage condition
A‐B | Padding Elevation | Related Drawing | Form No. 01 | H | RA
 Check the Padding elevation
A‐C | Pre‐Erection | Project Specification & DWG | Form No. 19 | H | H
 Release from Civil/Stl.Str QC for installation Chipping Condition & Cleaning of Foundation Surface CL Marking on Foundation  Pocket Cleaning,Positioning & Length  Original Gasket Cheking (Vertical Pumps) Barrel/Soleplate Leveling/Positioning (Vertical Pumps) Anchor Bolts Checked As Per Drawing Backfilling Completed
A‐D | Equipment Erection | Project Specification & DWG | Form No. 20 Form No. 22 Form No. 23 Form No. 24 | H | W
Orientation and Location Check Elevation & Leveling of Skid/Base Frame Checking Anchor bolt projection,tightening and shim plate filling
A‐E | Pocket Grouting | Project Specification & DWG | Form No. 21 | H | H
 Preparation Condition, Pocket Cleaning/Blowing, Water Socking, Grouting Material Verification, Pouring Water Temperature, Drain(if required) Anchor Bolt Projection & Direction  Mixing and pouring  Curing
NO. | INSPECTION/TEST ITEM | Reference Documents | Verifying Document | INSPECTION POINT |  | Remark
|  |  |  | CONTRACTOR | COMPANY
A‐F | Pre-Alignment | Project Specification | Form No. 25 | H | H
 Bolt Tightening  Leveling (Discharge Flange) Angular Alingment  Radial Alingment  Run Out  DBSE  Axial Movement
A‐G | Preservation | Project Specification & DWG | Form No. 26 | H | SW
 Preventing From Dust & Soil  Oil Level  Machine Surface Greasing Shaft Rotation Damage Preventing
A-H | Final Grouting (Skid Filling) | Project Specification & DWG | Form No. 05 | H | H
|  Preparation Condition,Cleaning/Blowing, Water Socking, GroutingMaterial Verification, Pouring WaterTemperature, Drain(if required) Shim plate Spot welding(If required)٭  Mixing and pouring  Curing Final surface condition |  |  |  | H
A-I | Anchor Bolt Tightening | Project Specification & DWG | Form No. 06 | H | H
A-J | Final Alignment (After Piping Reinstatement) | MTC & Project Specification & DWG | Form No. 27 | H | H
Angular Alingment  Radial Alingment  Run Out  DBSE  Soft Foot  Flange Parallelism& Bolt Tightening  Gasket Installation
A-K | All Necessary Appurtenance Installation | Project Specification & DWG | Form No.06 Form No G. 01 | H | SW
 Arrangment  Bolt Tightening
NO. | INSPECTION/TEST ITEM | Reference Documents | Verifying Document | INSPECTION POINT |  | Remark
|  |  |  | CONTRACTOR | COMPANY
B | Over Head/Gantry Crane
B-A | Equipment / Material check | Project Specification & DWG | Form No. 16 | H | W
B-B | Steel Structure Crane Girder | MTC & Project Specification & DWG | Form No. 28 | H | SW
Leveling
B‐C | Rail Installation/Welding | Project Specification & DWG | Form No. 29 Form No. 30 Form No. 31 | H | SW
Welding WPS/PQR Crane Span Dimention(Each 2 m) Position of Rail Seen in Plan Position of Rail Seen in Elev.  Position of Rail in Relative to One Another Position iof The End Buffers Relative to One Another RailExpandion Gap
B‐D | Bolt Tightening | Project Specification & DWG | Form No. 06 | H | SW
Rail Bolts For A Line(If Required) Rail Bolts For B Line(If Required) Crane Beam Hoist & Motor Crane Stopper Platform & Ladder Support For Electric Cable
B-E | Load Test | Project Specification & DWG | Form No. 32 | H | H
Bending Test (Nominal Load) Dynamic Test (110% of Nominal Load) Static Test (110% of Nominal Load) Inspection Of Electrical Cable Termination  Load Test Documentation
B-F | Final Inspection | Project Specification & DWG | Form No. 33 Form No. 34 | H | H
Punch List Clearing

## NOTE-01
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION / TEST NOTIFICATION
ACTIVITY : | [7 empty] | NOTIFICATION NO.:
DISCIPLINE : | [7 empty] | DATE :
CONTRACTOR: | [7 empty] | REF.DWG.NO. :
No | ACTIVITY DESCRIPTION |  |  |  |  | LOCATION |  | INSPECTION
[8 empty] | DATE & TIME | REMARKS
1
SR:
NOTE
RECEIVED BY: | INTERFACE (CONSTRUCTION): | CIVIL | YES |  | NO |  | SIGN.: …………………………... |  |  | DATE/TIME: ….……..…...…..
|  | MECH. | YES |  | NO |  | SIGN.: …………………………... |  |  | DATE/TIME: ….……..…...…..
|  | PIPING | YES |  | NO |  | SIGN.: …………………………... |  |  | DATE/TIME: ….……..…...…..
|  | ELEC. | YES |  | NO |  | SIGN.: …………………………... |  |  | DATE/TIME: ….……..…...…..
|  | INST. | YES |  | NO |  | SIGN.: …………………………... |  |  | DATE/TIME: ….……..…...…..
| CONTRACTOR : …………………………………......... | [8 empty] | DATE/TIME: ….……..…...…..
| COMPANY : ……………………………………….. | [8 empty] | DATE/TIME: ….……..…...…..
DISTRIBUTION:
|  |  | Company | [6 empty] | Contractor
FORM NO. : NOT-001

## 01
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Padding Leveling Check Report
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
Record :
Pad No. | Elevation |  | Dev. | Result |  | Pad No. | Elevation |  | Dev. | Result
| DWG | ACT |  | ACC | REJ |  | DWG | ACT |  | ACC | REJ
Remarks:
Contractor QA/QC |  |  | Survey Consultant |  |  |  | Company QA/QC
Name: Sign: Date: |  |  | Name: Sign: Date: |  |  |  | Name: Sign: Date:
Form No. 01

## 02
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Pre-Erection Inspection Report For Equipment Installation
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
* | RELEASE FROM CIVIL QC GROUP FOR ERECTION:
| NAME: |  | DATE: |  |  |  | SIGNATURE:
| Inspection Description |  |  | Acc. |  | Rej. | Remark
Foundation/STR Release
Backfilling Completion
Chipping Condition & Cleaning of Foundation Surface
Equipment Release Note
Anchor Bolt Cleaning/Greasing/Projection
Sliding Plate Verification
Sliding Saddle Cleaning/Greasing
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 02

## 03
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report for Horizontal Equipment Installation
REPORT NO.: |  |  | EQP. Tag No.: |  |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  |  | Date :
A
1.Vessel Coordinates :
CL |  | DWG | Actual | Diff.(mm) |  |  | Accept |  | Reject
A
B
C
D
2.Vessel Orientation:(mm)
0º - 180º |  |  |  |  | 90º - 270º
3.Elevation :
Reference point |  | DWG | Actual | Diff.(mm) |  |  | Accept |  | Reject | Point B
E
F
G
H
4.Equipment Slope (If Required):
Drawing |  |  | Actual |  |  |  | Accept |  | Reject
5.Nozzle Coordinates:
Nozzle No. | Size & Rating | Drawing |  | Actual |  | Diff.(mm) | Accept |  | Reject
6.Sliding Plate Installation:
Accept |  |  |  |  | Reject
Remark:
Contractor QA/QC |  |  | Survey Consultant |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  | Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 03
Natural CL
Length(TL TO TL): 13100
Fix side
AB
Slope:-

## 04
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report for Vertical Equipment Installation
REPORT NO.: |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
1.Vessel Height (TL TO TL):……………………………………
2.
Description | [5 empty] | Done |  | Not Done
Bolt Tightening
Shim plate Filling
3.Vessel Coordinates :
Drawing |  | Actual |  | Diff. |  | Accept |  | Reject
E: | N: | E: | N:
E: | N: | E: | N:
4.Nozzle Coordinates:
Nozzle No. | Size & Rating | Drawing |  | Actual |  | Accept |  | Reject
|  | E: | Act. E:
N:
El.:
|  | E: | Act. E:
N:
El.:
5.Plumbness:
Actual |  |  | Accept |  | Reject
(0.0-180):
(90-270):
Remark:
Contractor QA/QC |  |  | Survey Consultant |  |  |  | Company QA/QC
Name: Sign: Date: |  |  | Name: Sign: Date: |  |  |  | Name: Sign: Date:
Form No. 04
CL
TL
TL

## 05
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Grouting
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Material verification: |  | G2
G3
| Inspection Description |  |  | Acc. |  | Rej. | Remark
1. Cleaning of Surface (Grease, Rust,..)
2.Water Soaking (24 hrs before pouring)
3.Shim plate Filling
4.Shim plate Spot welding(If required)٭
5. Drain installation (if required)٭٭
6.Mixing Condition/Pouring
7.Curing
8. temperature
9. Final surface condition
٭ | For Over Three shim plate
٭٭ | At case of lack in fabrication
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 05

## 06
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Bolt Tightening
Contractor : |  |  |  | EQP. Tag No.: |  |  | Report No. :
DWG No. : |  |  |  | Location : |  |  | Date :
| No | Location |  | Bolt size /Material |  | Torque Wrench |  | Acc. | Reject
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 0

## 07
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Fit-Up
Contractor : |  |  | EQP. Tag No.: |  |  | Report No. :
DWG No. : |  |  | Location : |  |  | Date :
Specification No: |  | Typre of Joint : |  |  | Butt Weld |  | Lap joint
Material class:
[5 empty] | Lap joint |  | Seal Weld
| Inspected Item |  |  |  | Acc. |  | Rej.
Preparation Of Joint Bevel
Surface Cleaning
Correct Size & Shape Of Joint Seams
Remarks:
Contractor QA/QC |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  | Name: Sign: Date:
Form No. 07

## 08
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Visual Inspection Report For Welding Equipment(Repair&Recap)
Contractor : |  |  |  | EQP. Tag No.: |  | Report No. :
DWG No. : |  |  |  | Location : |  | Date :
| No | Weld Joint |  | Weld No. | NDT | Result | Remarks
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 08

## 09
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For External Accessories Installation
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Inspection Description |  |  | Acc. |  | Rej. | N/A | Remark
Plat Form Installation
Ladder Installation
Hand Rail Installation
Grating Installation
Safty Gate Installation
Bolt Tightening
Top Davit Installation
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 09

## 10
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION REPORT FOR INTERNAL CHECKING
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Inspection Description |  |  | Acc. |  | Rej. | Remark
Visual check of inside condition
Cleaning of inside surface
Corrosion checking
Inside Marking
Ventilation
Lightening
Scaffolding
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No.10

## 11
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INTERNAL INSTALLATION INSPECTION REPORT
Contractor : |  |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  |  | Location : |  |  |  | Date :
Description : |  | INTERNAL FILTER NOZZLE INSTALLATION FOR 85-FT-1203 A1
| Inspection Description |  |  |  | Acc. |  | Rej. | Remark
Internal Accessories Installation
Filter Nozzle Installation
Remarks:
Contractor QA/QC | [5 empty] | Company QA/QC
Name: Sign: Date: | [5 empty] | Name: Sign: Date:
Form No. 11

## 12
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INTERNAL INSTALLATION INSPECTION REPORT
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
Description :
| Inspection Description |  |  | Acc. |  | Rej. | Remark
GRAVEL
SAND
ANTHRACITE
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No.12

## 13
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION REPORT FOR TRAY MEASURMENT
Contractor : |  |  | EQP. Tag No.: |  |  | Report No. :
DWG No. : |  |  | Location : |  |  | Date :
Tray No.:
Items | Description |  |  | Dimensions |  | Tolerance | Result
1 | Tower internal condition
2 | Tower inside Diameter(A)
3 | Tray support leveling
4 | Tray support Distance
5 | Support beam and ring level/center/elevation
6 | Tray Diameter(B)
7 | Distance between tray and shell(C )
8 | Level of Tray(D)
9 | Height of baffle plate or outlet weir(F)
10 | Distance between tray and down comer(G)
11 | Height of Down comer(H)
12 | Down comer clearance
13 | Down comer top/bottom width
14 | BDH Valves Directions
15 | Tray Orientation Due to nozzles and Distributors
16 | Sagging of the Tray
17 | Bolt tightening control
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 13
H
D
F
B
C
G

## 14
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION REPORT FOR INTERNAL PACKING INSTALLATION
Contractor : |  |  |  | EQP. Tag No.: |  |  | Report No. :
DWG No. : |  |  |  | Location : |  |  | Date :
| No | Elevation Description |  | Material Type Verification |  | Acc. | Rej. | Remark
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 14

## 15
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION REPORT FOR PRESSURE VESSEL- TRAY LEAKAGE TEST
Contractor : |  |  |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  |  |  | Location : |  |  |  | Date :
Tray No. | Level |  |  | Holding Time |  | Leakage |  | Signature
| Tolerance | Act. |  |  |  | Tolerance | Act. | Contractor |  | Company | Operator
Reference Drawings:
The above tests have been witnessed by the vendors representative:
Signature:………………………….Name:………………………..
Date:……………………………….Vendor:………………………
Contractor QA/QC | [6 empty] | Company QA/QC
Name: Sign: Date: | [6 empty] | Name: Sign: Date:
FORM No. 15

## 16
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION REPORT FOR MATERIAL RECEIVING
Conractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
Vendor : |  |  | Discipline : |  |  |  | Date :
Certificate No.: |  |  | Quantity :
| Inspection Description |  |  | Contractor |  |  | Company
|  |  |  | Acc. |  | Rej. | Acc. | Rej.
Marking & Identification
Type and size
Tag & Name Plate
Preservation / Storage
Packing
Material Verification as Per Mill Certificate
Documents
Remark :
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 16

## 17
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
INSPECTION REPORT FOR INTERNAL FINAL BOX UP
Contractor : |  | EQP. Tag No.: |  | Report No. :
DWG No. : |  | Location : |  | Date :
Inspection Points |  |  |  |  | OK | N/A
1. Check all inlet and outlet nozzles for trash and debris.
2. Check internal piping and distributors for compliance with design and security of internal bolting.
3. Check structural adequacy of internal pipes, distributors, baffles, impingement plates and expansion allowances.
4. Check that internal gaskets have installed correctly.
5. Checking the installation of Demister Pads.
6. Check that tower is clean, free of debris and obstruction particularly at bottom out lets and pump suction lines.
7. Check all internals for compliance with design.
8. Number of Trays.
9. Type of trays.
10. Blanking Patterns.
11. Diameter and location of Drain holes.
12. Dimensions of seal pans and draw off boxes.
13. Location and sizes of tray man ways.
14. Drain holes clear.
15. Dividers correct.
16. Wire mesh material construction and installation are correct.
17. Check inlet nozzle extension.
18. Check Distributors orientation.
19. Check inlet distributors with design.
20. Make sure that down comers are not restricted by tray supports or anything else.
21. Check tray orientation due to nozzles and distributors.
22. Check dimensions of draw off pans.
23. Check for seal welding or joints of tray down comers, pans and draw off boxes.
24.For Packed beds check:
24-1.Bed location
24-2.Bed dimensions
24-3.bed packing
25. Check that tray supports have installed and welded correctly.
26.Check the Hold down devices for internal packing installed correctly.(pull rings, etc)
27. Check the orientations for V grid Trays.
28. Check for any abnormality such as pitting on gasket sealing surface of manhole flange.
29.check the Gasket according to DWG(for man hole closing)
30.Stud bolt Preservation
31.All connections blinded checking
32.Man hole Bolt tightening (Balanced)
Contractor QA/QC |  |  | Company QA/QC
Name: Sign: Date: |  |  | Name: Sign: Date:
FORM No. 17

## 18
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
MECHANICAL FINAL INSPECTION REPORT
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Inspection Description |  |  | Acc. |  | Rej. | Remark
All the Mechanical Documents completed
Visual checking for any Shortage and Damage
Sliding side Washer clearance(in horizontal Vessels)
Touch Up(if required)
External Installation completed
Name plate Verification
Grouting Final Surface Acceptance
Bolt /Nut Completion
Punch list Clear (if required)
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 09

## 19
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Pre-Erection Inspection Report For Equipment Installation
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
* | RELEASE FROM CIVIL QC GROUP FOR ERECTION:
| NAME: |  | DATE: |  |  |  | SIGNATURE:
| Inspection Description |  |  | Acc. |  | Rej. | Remark
Center Line Marking on Foundation
Chipping Condition & Cleaning of Foundation Surface
Pocket Cleaning,Positioning & Length
Original Gasket Cheking (Vertical Pumps)
Barrel/Soleplate Leveling/Positioning (Vertical Pumps)
Anchor Bolts Checked As Per Drawing
Backfilling Completed
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 19

## 20
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Barrel/Sole Plate Erection
REPORT NO.: |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  | Location : |  |  |  | Date :
Position:
CL | DWG | Actual | Diff.(mm) |  | Accept |  | Reject
A
B
Elevation:
Reference point | DWG | Actual | Diff.(mm) |  | Accept |  | Reject | Point B
E
F
G
H
Remark:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  | Date: |  |  | Sign:
Contractor QA/QC |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  | Name: Sign: Date:
Form No.20

## 21
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Pocket Grouting
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Grout Type: |  | G2 |  | G3
Brand Name:
| Inspection Description |  |  | Acc. |  | Rej. | Remark
1. Pocket Cleaning & Air Blowing (No Grease, Rust,..)
2.Water Soaking (24 hrs before pouring)
3.Anchor Bolt Projection & Direction
4.Grouting Material Verification ( Brand,Type & Expire Date)
6.Mixing Condition/Pouring
7.Temperature
8. Curing ( After Grouting)
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 21

## 22
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Barrel /Sole Plate Leveling
REPORT NO.: |  | EQP. Tag No.: |  |  |  |  | Report No. :
DWG No. : |  | Location : |  |  |  |  | Date :
1.Leveling(Diagonal On Machine Surface) :
CL | Tolerance |  | Actual Readings |  |  | Accept |  | Reject
EAST
NORTH
2.Bolt Tightening (Diagonal) :
Accept |  |  |  | Reject
3.Shim Plate Filling (Carbon Steel / Stainless Steel)
Reference point | DWG | Actual | Diff.(mm) | Reject |  | Accept |  | Reject | Point B
Remark:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  | Date: |  |  |  | Sign:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 22

## 23
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Equipment Erection
REPORT NO.: |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
C
PLANT NORTH |  | E |  |  |  |  | G
| B | [7 empty] | A
|  | F |  |  |  |  | H
D
Position:
CL |  | DWG | Actual | Diff.(mm) |  | Accept |  | Reject
A
B
C
D
Elevation:
CL |  | DWG | Actual | Diff.(mm) |  | Accept |  | Reject
Suction
Discharge
Top Base Frame Elevation:
Reference point |  | DWG | Actual | Diff.(mm) |  | Accept |  | Reject | Point B
E
F
G
H
Remark:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  |  | Date: |  |  | Sign:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 23
BASE FRAME

## 24
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Vertical Pump Leveling
REPORT NO.: |  | EQP. Tag No.: |  |  |  |  | Report No. :
DWG No. : |  | Location : |  |  |  |  | Date :
1.Original Gasket Installation (If Required) :
Accept |  |  |  | Reject
2.Leveling(Diagonal On Machine Surface) :
CL | Tolerance |  | Actual Readings |  |  | Accept |  | Reject
EAST
NORTH
3.Bolt Tightening (Diagonal) :
Accept |  |  |  | Reject
Remark:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 24

## 25
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Pre Alignment
REPORT NO.: |  | EQP. Tag No.: |  |  |  |  | Report No. :
DWG No. : |  | Location : |  |  |  |  | Date :
1.Bolt Tightening Checking ( Driver & Driven Base ) : |  |  | Done |  |  | Not Done
2.Sketch
3.Leveling(Machine Surface) :
CL | Tolerance |  | Actual Reading |  |  | Accept |  | Reject
NORTH-SOUTH
EAST-WEST
4.Shaft Alignment (Acceptable Tolerance) :
CL | RADIAL |  | AXIAL |  |  | Accept |  | Reject
| R1 | R2 | A1 |  | A2
0°
90°
180°
270°
0°
5.Distance Between Shaft Ends (DBSE) (Acceptable Tolerance) :
DBSE ACORDING TO DWG |  | ACTUAL DBSE ON POSITION 0° |  |  |  | SPACER LENGTH
6. Run out (Acceptable Tolerance) :
| 0° |  | 90° |  |  | 180° |  | 270°
DRIVER
7. Axial Movement :
DRIVER |  |  | DRIVEN
Remark:
Contractor QA/QC |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  | Name: Sign: Date:
Form No. 25

## 26
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Preservation
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Inspection Description |  |  | Acc. |  | Rej. | Remark
1.Physical Protection
2.Dust Preventing Cover
3.Oil Filling & Oil Level Checking
4.Machine Sureface Greasing
5.Shaft Rotation Log Sheet Compeletion
6.Suction/Discharg Blinding & Protection
7.Touch Up
* There is a Shortage Item as Belows :
* There is a Damage Items as Belows:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 26

## 27
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Final Shaft Alignment
REPORT NO.: |  | EQP. Tag No.: |  |  |  |  | Report No. :
DWG No. : |  | Location : |  |  |  |  | Date :
1.Bolt Tightening Checking ( Driver & Driven Base ) : |  |  | Done |  |  | Not Done
2.Sketch
3.Leveling(Machine Surface) :
CL | Tolerance |  | Actual Reading |  |  | Accept |  | Reject
NORTH-SOUTH
EAST-WEST
4.Shaft Alignment (Acceptable Tolerance) :
CL | RADIAL |  | AXIAL |  |  | Accept |  | Reject
| R1 | R2 | A1 |  | A2
0°
90°
180°
270°
0°
5.Distance Between Shaft Ends (DBSE) (Acceptable Tolerance) :
DBSE ACORDING TO DWG |  | ACTUAL DBSE ON POSITION 0° |  |  |  | SPACER LENGTH
6. Run out (Acceptable Tolerance) :
| 0° |  | 90° |  |  | 180° |  | 270°
DRIVER
7. Axial Movement :
DRIVER |  |  | DRIVEN
8. Soft Foot :
Accept |  |  | Reject
Remark:
Contractor QA/QC |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  | Name: Sign: Date:
Form No.27

## 28
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Traveling Beam Leveling
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
A Line | [5 empty] | B Line
Tolerance | Every 2m = |  |  |  |  | Tolerance | Every 2m =
Check Point | Level Reading |  | ACC | REJ |  | Check Point | Level Reading | ACC | REJ
1 | [5 empty] | 1
2 | [5 empty] | 2
3 | [5 empty] | 3
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Remarks:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  |  | Date: |  | Sign:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 28

## 29
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Rail Span Dimensions
Contractor : |  |  | EQP. Tag No.: |  |  | Report No. :
DWG No. : |  |  | Location : |  |  | Date :
SPAN DISTANCE : |  |  | TOLERANCE:
Span No. | Distance | Diff(mm) | ACC | REJ
A
B
C
D
E
F
Design Span :
Remarks:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  |  | Date: |  | Sign:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 29

## 30
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Rail Positioning
Contractor : |  |  | EQP. Tag No.: |  |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  |  | Date :
Point No. | Coordinates |  | Line A |  |  |  | Line B
|  |  | Design | Actual | Diff(mm) |  | Design | Actual | Diff(mm)
A | EAST
NORTH
B | EAST
D | NORTH
C | EAST
F | NORTH
D | EAST
B | NORTH
E | EAST
D | NORTH
F | EAST
F | NORTH
Remarks:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  |  | Date: |  |  | Sign:
Contractor QA/QC | [5 empty] | Company QA/QC
Name: Sign: Date: | [5 empty] | Name: Sign: Date:
Form No. 30

## 31
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Inspection Report For Rail Elevation
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
DESIGN SPAN:
Point No. | Line | Elevation |  | ACC | REJ
|  | Design | Actual
A | Line A
Line B
B | Line A
D | Line B
C | Line A
F | Line B
D | Line A
B | Line B
E | Line A
D | Line B
F | Line A
F | Line B
Remarks:
READINGS APPROVED BY CONTRACTOR SURVEY:
Name: |  |  | Date: |  |  | Sign:
Contractor QA/QC | [5 empty] | Company QA/QC
Name: Sign: Date: | [5 empty] | Name: Sign: Date:
Form No. 31

## 32
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Final Inspection Report For Overhead Crane Installation
Contractor : |  |  |  | EQP. Tag No.: |  |  | Report No. :
DWG No. : |  |  |  | Location : |  |  | Date :
L=
| Inspection Description |  |  | Weight Of Test | Time Of Test | Deflection Before Loading | Deflection After Loading | Acc. | Rej. | Remark
DYNAMIC TEST (1.1 Of Nominal Loader Vendor Recommendation)
STATIC TEST (1.25 Of Nominal Loader Vendor Recommendation)
Remarks:
Contractor QA/QC | [5 empty] | Company QA/QC
Name: Sign: Date: | [5 empty] | Name: Sign: Date:
Form No. 32

## 33
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Final Inspection Report For Overhead Crane Installation
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Inspection Description |  |  | Acc. |  | Rej. | Remark
Installation of Crane Girder
Rail Installation
End buffers Installation
Bolt Tightening
Hoist & Motor Installation
Load Test
Accessories Installation
Cleaning Checking ( Oil, Grease, Paint, Debris,… )
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 33

## 34
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
FINAL INSPECTION REPORT AND PUNCH LIST
Contractor : |  |  | EQP. Tag No.: |  |  |  | Report No. :
DWG No. : |  |  | Location : |  |  |  | Date :
| Punch Description |  | Category |  |  | Done | Not Done | Remarks
|  |  | A | B
Remarks:
Contractor QA/QC |  |  |  |  | Company QA/QC
Name: Sign: Date: |  |  |  |  | Name: Sign: Date:
Form No. 34

## G-01
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
GENERAL INSPECTION REPORT
Contractor : |  | EQP. Tag No.: |  | Report No. :
DWG No. : |  | Location : |  | Date :
Description :
(THIS INSPECTION REPORT TO BE USED FOR UN-SPECIFIED ITEMS WHICH MAY BE REQUIRED FOR REPORTING DURING CONSTRUCTION, AND IT WILL BE FILLED BASED ON THE OCCURRED EVENT / INSPECTION)
Remarks:
Contractor QA/QC |  |  | Company QA/QC
Name: Sign: Date: |  |  | Name: Sign: Date:
Form No. G-01

## 08 (2)
Kangan Utility & Offsite Project (Phase II)
Inspection And Test Plan For Mechanical Activities
Contract No. : 99/158
Visual Inspection Report For Welding flange parallel (Repair&Recap)
Contractor : |  | ZOLAL IRAN |  | EQP. Tag No.: | 85_PT_2201A |  | Report No. : | KP_ZO_85_QC_MA_0184
DWG No. : |  | VP_85_22_MA_0005_0122 |  | Location : | 85 |  | Date : | 2024-06-01
| No | Spool Number |  | Weld No. |  | NDT | Result | Remarks
| 1 | PT 06 |  | FLANGE UP |  | N/A
| 2 | PT 06 |  | FLANGE DOWN |  | N/A
3
4
5
6
7
8
Remarks:
Contractor QA/QC | [5 empty] | Company QA/QC
Name: Sign: Date: | [5 empty] | Name: Sign: Date:
Form No. 08